## TEMPLATE
Academic Year 2025-2026 |  |  |  | Pro Tip ➜ |  |  |  |  | USE THE 'FILL CELL' OPTION TO INDICATE WHEN YOU WILL BE ADDRESSING EACH ITEM. SEE EXAMPLES.
DEGREE TYPE | [19 empty] | DATE | [29 empty] | By signing this document, I affirm that the timeline shown is reasonably accurate and achievable.
STUDENT NAME & ID: | [19 empty] | Student signature:
ADVISOR NAME | [19 empty] | Advisor signature:
PHASE |  | DETAILS | Complete or not applicable | SUMMER | [11 empty] | FALL | [15 empty] | SPRING | [15 empty] | SUMMER
| PROJECT STAGE: | Week of the month ➡️ |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEPT |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Complete research/data collection/ analysis/lit review etc as appropriate to your thesis, dissertation or project | Literature Review
Data Collection
Data Analysis
2 | Initial Draft of Paper and Defense planning | Paper outline
1st draft
Review draft with advisor
Add'l drafts and review
Schedule defense date, time, location *PhD students request outside examiner
3 | Defense and Corrections | Defend thesis, dissertation, project
Post-defense corrections
Draft review with advisor
Additional corrections
4 | Final draft and committee, department chair, and dean's office approvals | Final draft
Draft approval by committee
Dept chair review (CHECK THEIR DEADLINES!)
School/College Dean review* (CHECK THEIR DEADLINES!)
5 | Make grad school corrections, submit final paperwork, graduation requirements | Submit to Grad School
Complete final paperwork/forms
Make Grad School corrections (thesis/dissertation only)
GRADUATE!!!!
| *Only applies to thesis/dissertation students, not project students |  |  | JUL 1: GRAD SCHOOL SUBMISSION DEADLINES; OCT 2: FALL; JAN 1: SPRING; MAY 1: SUMMER
[8 empty] | THESIS/DISSERTATION: | [12 empty] | 2018-11-28 | [10 empty] | 2018-04-07 | [15 empty] | 2018-08-01
[8 empty] | PROJECT: | [12 empty] | 2018-12-15 | [10 empty] | 2018-04-24 | [15 empty] | 2018-08-10

## EXAMPLE-Spring
ACADEMIC |  |  |  |  | Smartsheet Tip ➜ |  |  |  |  | EXAMPLE FOR SPRING GRADUATION
DEGREE TYPE |  | Ph.D. | [18 empty] | DATE | [5 empty] | DD MM YYYY | [23 empty] | By signing this document, I affirm that the timeline shown is reasonably accurate and achievable
STUDENT NAME & ID: |  | Bruce Banner, 31234566 | [18 empty] | Student signature:
ADVISOR NAME |  | Natasha Romanoff, 31234567 | [18 empty] | Advisor signature: | [7 empty] | Natasha Romanoff
PHASE |  |  | DETAILS | Complete or not applicable | SUMMER | [11 empty] | FALL | [15 empty] | SPRING | [15 empty] | SUMMER
| PROJECT STAGE: |  | Enter the date of the first Monday of each month --> |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEPT |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Complete research/data collection/ analysis/lit review etc as appropriate to your thesis, dissertation or project |  | Literature Review
Data Collection
Data Analysis
2 | Initial Draft of Paper and Defense planning |  | Paper outline
1st draft | bar: NOV 4 to DEC 2
Review draft with advisor | bar: DEC 3 to DEC 4
Add'l drafts and review | bar: JAN 1
Schedule defense date, time, location | bar: JAN 2
Request Outside Examiner (PHD ONLY) | bar: JAN 3
3 | Defense and Corrections |  | Defend thesis, dissertation, or project | bar: JAN 4
Post-defense corrections | bar: FEB 1
Draft review with advisor | bar: FEB 1 to FEB 2
Add'l corrections | bar: FEB 2
4 | Final draft and committee, department chair and dean's office approvals |  | Final draft | bar: FEB 2
Draft approval by committee | bar: FEB 3
Dept chair review | bar: FEB 4 to MAR 1
School/College Dean review | bar: MAR 1 to MAR 3
5 | Make grad school corrections, submit final paperwork, graduation requirements. |  | Submit to Grad School | bar: MAR 4 to APR 3
Complete final paperwork/forms | bar: APR 1 to APR 3
Make grad school corrections (thesis/dissertation only) | bar: APR 3 to APR 4
GRADUATE!!!!

## EXAMPLE-Summer
ACADEMIC |  |  |  |  | Smartsheet Tip ➜ |  |  |  |  | EXAMPLE FOR SPRING GRADUATION
DEGREE TYPE |  | Ph.D. | [18 empty] | DATE | [5 empty] | DD MM YYYY | [23 empty] | By signing this document, I affirm that the timeline shown is reasonably accurate and achievable
STUDENT NAME & ID: |  | Bruce Banner, 31234566 | [18 empty] | Student signature:
ADVISOR NAME |  | Natasha Romanoff, 31234567 | [18 empty] | Advisor signature: | [7 empty] | Natasha Romanoff
PHASE |  |  | DETAILS | Complete or not applicable | SUMMER | [11 empty] | FALL | [15 empty] | SPRING | [15 empty] | SUMMER
| PROJECT STAGE: |  | Enter the date of the first Monday of each month --> |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEPT |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Complete research/data collection/ analysis/lit review etc as appropriate to your thesis, dissertation or project |  | Literature Review
Data Collection
Data Analysis
2 | Initial Draft of Paper and Defense planning |  | Paper outline
1st draft | bar: FEB 4 to MAR 2
Review draft with advisor | bar: MAR 3 to MAR 4
Add'l drafts and review | bar: APR 1
Schedule defense date, time, location | bar: APR 2
Request Outside Examiner (PHD ONLY) | bar: APR 3
3 | Defense and Corrections |  | Defend thesis, dissertation, or project | bar: APR 4
Post-defense corrections | bar: MAY 1
Draft review with advisor | bar: MAY 1 to MAY 2
Add'l corrections | bar: MAY 2
4 | Final draft and committee, department chair and dean's office approvals |  | Final draft | bar: MAY 2
Draft approval by committee | bar: MAY 3
Dept chair review | bar: MAY 4 to JUN 1
School/College Dean review | bar: JUN 1 to JUN 3
5 | Make grad school corrections, submit final paperwork, graduation requirements. |  | Submit to Grad School | bar: JUN 4 to JUL 3
Complete final paperwork/forms | bar: JUL 1 to JUL 3
Make grad school corrections (thesis/dissertation only) | bar: JUL 3 to AUG 2
GRADUATE!!!! | bar: AUG 3 to AUG 4

## EXAMPLE-Fall
ACADEMIC |  |  |  |  | Smartsheet Tip ➜ |  |  |  |  | EXAMPLE FOR SPRING GRADUATION
DEGREE TYPE |  | Ph.D. | [18 empty] | DATE | [5 empty] | DD MM YYYY | [23 empty] | By signing this document, I affirm that the timeline shown is reasonably accurate and achievable
STUDENT NAME & ID: |  | Bruce Banner, 31234566 | [18 empty] | Student signature:
ADVISOR NAME |  | Natasha Romanoff, 31234567 | [18 empty] | Advisor signature: | [7 empty] | Natasha Romanoff
PHASE |  |  | DETAILS | Complete or not applicable | SUMMER | [11 empty] | FALL | [15 empty] | SPRING | [15 empty] | SUMMER
| PROJECT STAGE: |  | Enter the date of the first Monday of each month --> |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEPT |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Complete research/data collection/ analysis/lit review etc as appropriate to your thesis, dissertation or project |  | Literature Review
Data Collection
Data Analysis
2 | Initial Draft of Paper and Defense planning |  | Paper outline
1st draft | bar: JUN 4 to JUL 2
Review draft with advisor | bar: JUL 3 to JUL 4
Add'l drafts and review | bar: AUG 1
Schedule defense date, time, location | bar: AUG 2
Request Outside Examiner (PHD ONLY) | bar: AUG 3
3 | Defense and Corrections |  | Defend thesis, dissertation, or project | bar: AUG 4
Post-defense corrections | bar: SEPT 1
Draft review with advisor | bar: SEPT 1 to SEPT 2
Add'l corrections | bar: SEPT 2
4 | Final draft and committee, department chair and dean's office approvals |  | Final draft | bar: SEPT 2
Draft approval by committee | bar: SEPT 3
Dept chair review | bar: SEPT 4 to OCT 1
School/College Dean review | bar: OCT 1 to OCT 3
5 | Make grad school corrections, submit final paperwork, graduation requirements. |  | Submit to Grad School | bar: OCT 4 to NOV 3
Complete final paperwork/forms | bar: NOV 1 to NOV 3
Make grad school corrections (thesis/dissertation only) | bar: NOV 3 to DEC 2
GRADUATE!!!! | bar: DEC 3 to DEC 4